## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | User Account Management | 4.2.4.1 | Open User Account | Design the registartion form | 2019-09-30 | 2019-09-30 | Complete | Abhijeet
2 | User Account Management | 4.2.4.1 | Open User Account | Implement the code using Firbase | 2019-09-30 | 2019-10-01 | Complete | Abhijeet
3 | User Account Management | 4.2.4.1 | Open User Account | Test the firebase setup and account creation functionality | 2019-10-01 | 2019-10-01 | Complete | Abhijeet
4 | User Account Management | 4.2.4.2 | Login Into Account | Design the login page | 2019-10-01 | 2019-10-01 | Complete | Abhijeet
5 | User Account Management | 4.2.4.2 | Login Into Account | Implement the login code | 2019-10-01 | 2019-10-01 | Complete | Murtaza
6 | User Account Management | 4.2.4.2 | Login Into Account | Test the login-logout functionality | 2019-10-01 | 2019-10-02 | Complete | Murtaza
7 | User Account Management | 4.2.4.3 | Sign Up using Existing Accounts. | Implement the Firebase logic | 2019-10-02 | 2019-10-03 | Complete | Murtaza
8 | User Account Management | 4.2.4.3 | Sign Up using Existing Accounts. | test the functionalty | 2019-10-03 | 2019-10-03 | Complete | Murtaza
9 | User Account Management | 4.2.4.4 | Modify User Information. | Implement the GUI for user account modifications | 2019-10-04
10 | User Account Management | 4.2.4.4 | Modify User Information. | Implement the code | 2019-10-04
11 | User Account Management | 4.2.4.4 | Modify User Information. | test the functionalty | 2019-10-05
12 | User Account Management | 4.2.4.1 | Edit Account Details | Display a form to Edit Account Details | 2019-10-06
13 | User Account Management | 4.2.4.1 | Edit Account Details | Create an update and submit button | 2019-10-06
14 | User Account Management | 4.2.4.1 | Edit Account Details | Implement core functionality | 2019-10-07
15 | User Account Management | 4.2.4.1 | Edit Account Details | Implement GUI requirments | 2019-10-07
16 | User Account Management | 4.2.4.1 | Edit Account Details | Develop test Cases for Edit Account Details functionality | 2019-10-08
17 | Order Management | 4.2.1.1. | Search Content | Find the API for Menu | 2019-10-02 | 2019-10-02 | Complete | Ansley
18 | Order Management | 4.2.1.1. | Search Content | Implement the API | 2019-10-03 | 2019-10-03 | Complete | Ansley
19 | Order Management | 4.2.1.2 | Customize Order | Add code to let user modify the order | 2019-10-08
20 | Order Management | 4.2.1.2 | Customize Order | test the functionalty | 2019-10-08
21 | Order Management | 4.2.1.3 | Cancel Order | Implement the cancel functionality | 2019-10-09
22 | Order Management | 4.2.1.3 | Cancel Order | test the functionalty | 2019-10-10
23 | Delivery Management | 4.2.2.2 | Change delivery address | Add modify option for delivery detail | 2019-10-11
24 | Delivery Management | 4.2.2.2 | Change delivery address | test the functionalty | 2019-10-12
25 | Delivery Management | 4.2.2.3 | Add delivery instruction | Add additional free text box for adding instructions | 2019-10-13
26 | Delivery Management | 4.2.2.3 | Add delivery instruction | test the functionalty | 2019-10-14
27 | Payment Management | 4.2.5.1 | Make Payment | Design a form for payement functionality | 2019-10-15
28 | Payment Management | 4.2.5.1 | Make Payment | Find out third party gateway that can be used for payement | 2019-10-16
29 | Payment Management | 4.2.5.1 | Make Payment | Implement the payement logic | 2019-10-17
30 | Payment Management | 4.2.5.1. | Make Payment | test the payment functionality | 2019-10-18
31 | Payment Management | 4.2.5.2 | Add Payment Details | Design a form and implement the form | 2019-10-19
32 | Payment Management | 4.2.5.2 | Add Payment Details | test the functionalty | 2019-10-20
33 | Notification Management | 4.2.6.1 | Order Recipets | Developed logic to trigger email with order recipets to user | 2019-10-21
34 | Notification Management | 4.2.6.1 | Order Recipets | Test if email is getting triggered on placing an order | 2019-10-22
35 | Customer Support | 4.2.7.1 | Feedback and Suggestions | Design a form to accept the feedback and suggestions | 2019-10-23
36 | Customer Support | 4.2.7.1 | Feedback and Suggestions | Implement the logic | 2019-10-24
37 | Customer Support | 4.2.7.1 | Feedback and Suggestions | Test if user can give feedback or suggestions | 2019-10-25

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | User Account Management | 4.2.4.1 | Open User Account | Improve the look and feel of the GUI | 2019-11-08
2 | User Account Management | 4.2.4.1 | Open User Account | test the functionalty for all the negative test casses | 2019-11-10
3 | User Account Management | 4.2.4.2 | Login Into Account | Improve the look and feel of the GUI | 2019-11-11
4 | User Account Management | 4.2.4.2 | Login Into Account | test the functionalty for all the negative test casses | 2019-11-12
5 | User Account Management | 4.2.4.3 | Sign Up using Existing Accounts. | Improve the look and feel of the GUI | 2019-11-13
6 | User Account Management | 4.2.4.3 | Sign Up using Existing Accounts. | test the functionalty for all the negative test casses | 2019-11-14
7 | User Account Management | 4.2.4.1 | Edit Account Details | Improve the look and feel of the GUI | 2019-11-15
8 | User Account Management | 4.2.4.1 | Edit Account Details | test the functionalty for all the negative test casses | 2019-11-16
9 | Order Management | 4.2.1.2 | Customize Order | Improve the look and feel of the GUI | 2019-11-18
10 | Order Management | 4.2.1.2 | Customize Order | test the functionalty for all the negative test casses | 2019-11-19
11 | Order Management | 4.2.1.3 | Cancel Order | Improve the look and feel of the GUI | 2019-11-20
12 | Order Management | 4.2.1.3 | Cancel Order | test the functionalty for all the negative test casses | 2019-11-24
13 | Delivery Management | 4.2.2.3 | Add delivery instruction | Improve the look and feel of the GUI | 2019-11-25
14 | Delivery Management | 4.2.2.3 | Add delivery instruction | test the functionalty for all the negative test casses | 2019-11-26
15 | Payment Management | 4.2.5.1 | Make Payment | Improve the look and feel of the GUI | 2019-11-27
16 | Payment Management | 4.2.5.1 | Make Payment | test the functionalty for all the negative test casses | 2019-12-01
17 | Notification Management | 4.2.6.1 | Order Recipets | Improve the look and feel of the GUI | 2019-12-02
18 | Notification Management | 4.2.6.1 | Order Recipets | test the functionalty for all the negative test casses | 2019-12-03
19 | Customer Support | 4.2.7.1 | Feedback and Suggestions | Improve the look and feel of the GUI | 2019-12-04
20 | Customer Support | 4.2.7.1 | Feedback and Suggestions | test the functionalty for all the negative test casses | 2019-12-05