## Sheet1
Color Coding |  | Completed |  |  |  |  | SPRING 2018 SEMESTER
[7 empty] | January | feb
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
[6 empty] | Date | 2019-01-29 | 2019-02-12 | 2019-02-19 | 2019-02-26 | 2019-03-05 | 2019-03-12 | 2019-03-19 | 2019-03-26 | 2019-04-02 | 2019-04-09 | 2019-04-16 | 2019-04-23 | 2019-04-30 | 2019-05-07 | 2019-05-14
Project Phase | Activity |  | Resource Type | Start Date | End Date | Progress %
Project Initiation | Project proposal discussion |  | Sukhada Sheth | 2019-01-29 | 2019-02-05 | 100%
| Prioritize project ideas |  | Ansley Rodrigues | 2019-02-05 | 2019-02-12 | 100%
| Estimation of cost and schedule |  | Sukhada Sheth | 2019-02-05 | 2019-02-12 | 100%
| Development of the business case |  | Sukhada Sheth | 2019-02-05 | 2019-02-12 | 100%
| Project environment preparation |  | Ansley Rodrigues | 2018-02-08 | 2018-02-19 | 100%
MILESTONE 1: INITIAL PROJECT PLAN
Requirement Analysis | Production of project schedule |  | Sukhada Sheth | 2019-02-12 | 2018-02-19 | 100%
| Determine project features |  | Sukhada Sheth | 2019-02-12 | 2019-02-12 | 100%
| Organize Project Team |  | Sukhada Sheth | 2019-01-29 | 2019-02-05 | 100%
| Definition of Software Methodology |  | Ansley Rodrigues | 2019-01-29 | 2017-02-12 | 100%
| Gathering of Business Requirements |  | Vijay Shah | 2019-02-19 | 2019-02-26 | 100%
| Business Requirements Analysis |  | Vijay Shah | 2019-02-12 | 2019-02-19 | 100%
| System Requirements definition |  | Ansley Rodrigues | 2019-02-20 | 2019-02-27 | 100%
| BRM Diagram, User Roles , Context Diagram, System Interface Table , Requirements Types |  | Vijay Shah | 2019-03-05 | 2019-03-12 | 100%
| Business Requirements, Functional Decomposition, Fishbone Diagrams , RCT |  | Vijay Shah | 2019-03-12 | 2019-03-19 | 100%
| UML analysis diagrams (use case, activity diagrams) , Data-flow Diagram (logical) , Functional Requirements (user stories) |  | All team members | 2019-03-19 | 2019-03-26 | 100%
| Requirements prioritization |  | Sukhada Sheth | 2019-03-12 | 2019-03-19 | 0%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design |  | Murtaaza Roondiwala | 2019-03-26 | 2019-04-02 | 0%
| Database Design |  | Abhijit Tambe | 2019-03-26 | 2019-04-02 | 0%
| System Interface Design |  | Murtaaza Roondiwala | 2019-03-19 | 2019-03-26 | 100%
| User interface design |  | Murtaaza Roondiwala | 2019-03-19 | 2019-03-26 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Home | GUI & Functionality Design | Ansley | 2019-04-02 | 2019-04-03 | 0%
|  | Coding | Abhjit Tambe | 2019-04-04 | 2019-04-06 | 0%
| Search Items | GUI & Functionality Design | Ansley | 2019-04-07 | 2019-04-08 | 0%
|  | Coding | Murtaaza Roondiwala | 2019-04-09 | 2019-04-15 | 0%
| Payement Management | GUI & Functionality Design | Ansley | 2019-04-09 | 2019-04-10 | 0%
|  | Coding | Sukhada Sheth | 2019-04-13 | 2019-04-16 | 0%
MILESTONE 4: CODING COMPLETED
Integration & Testing | Overall Testing Strategy |  |  | 2019-04-23 | 2019-04-24 | 0%
| Evaluate Features to be Tested |  | ALL | 2019-04-24 | 2019-04-25 | 0%
| Home | Design Test Cases | Ashish Dwivedi | 2019-04-25 | 2019-04-26 | 0%
|  | Execute Test Cases | Ashish Dwivedi Chuangyu Cheng | 2019-04-26 | 2019-04-27 | 0%
|  | Anaylze Test Results | ALL | 2019-04-27 | 2019-04-28 | 0%
| Payement Management | Design Test Cases | Ashish Dwivedi | 2019-04-27 | 2019-04-28 | 0%
|  | Execute Test Cases | Ashish Dwivedi Chuangyu Cheng | 2019-04-28 | 2019-04-29 | 0%
|  | Anaylze Test Results | ALL | 2019-04-30 | 2019-05-01 | 0%
| Search Items | Design Test Cases | Ashish Dwivedi | 2019-04-30 | 2019-05-01 | 0%
|  | Execute Test Cases | Ashish Dwivedi Chuangyu Cheng | 2019-05-01 | 2019-05-02 | 0%
|  | Anaylze Test Results | ALL | 2019-05-03 | 2019-05-04 | 0%
Fixing Issues | All the modules |  | Respective Module Owner | 2019-04-27 | 2019-05-04 | 0%
Implementation | Deploy Application For Presentation Demo |  | All | 2019-05-04 | 2019-05-06 | 0%
MILESTONE 5: TESTING COMPLETED
Presentation | Prepare Presentation of Demo |  | ALL | 2019-05-07 | 2019-05-14